## Read Me
Tab Name | Notes
Overview | Overview of what the project is about and the deliverables
Imp Links | Add all links related to the project and keep updating this tab with new/useful links.
Steps+Norms | Mention all the steps with details, role allocated for the step, unit of work, norms in mandays, buffer days and define which steps can run parallelly.
Team | Team roles and leaves will be captured here.
Bandwidth Plan | We calculate the bandwidth here, based on the norms defined in steps & norms tab.
Project Plan | This is the master tab where we have the planned dates for each step till last step
Workload Tracker | This tab helps to see the work load on each team member.
Enhanced Dashboard | This will give you a summary view of all the major milestones we are going to cover in this project week wise.
Flat Task Log (Helper Sheet) | This is capturing all the allocations of the team daily, so that the subject team does not need to create any different tab internally to allocate tasks.

## Overview
Project Name
Project Description: | Rebrand print and digital resources (MP4, PDF, HTML, Print Book) by removing the existing Pearson references (logo or watermark or credits). The update is required because Pearson branding cannot be used from AY26-27 onwards.
Key Objectives: | Eliminate all references to the Pearson brand.
Stakeholders: | DTP Team Design Team IR/Media Team Legal/Compliance Epub Vendor Category team PM team QA team
Additional Notes:
Deliverables: | 567 Books to be Rebranded and Ready for RIPing
Target Delivery Date: | 2025-12-15

## Imp Links
Have all the important links of the documents related to this project in this tab. It could be spreadsheet, ppt, word document, pdf files, folder links, etc.
Important Links
Document Description | Link
paste the link here
| paste the link here | This is Science prompt.
paste the link here
paste the link here
| paste the link here | What is the purpose? please bucket these links under right categories as is done in nin and shikar and explain where needed
Have you included getting permissions in your list of you are referring to FBS listening texts? some texts require permissions. how and where is that check happening?
Pearson source files for what? please write proper descriptions
Latest textbooks of?
What is SA ? SA of?
Broad guidelines of? please write proper headings

## Validations
[9 empty] | Fill in this column and column R | Fill in this column and column S | Steps | Role | Milestone | Milestone#
List all ROLES, UNITS, Norms that you want to use in steps+norms tab here. You can edit it. |  |  | List all TERM, CLASS, CH/UNIT NO., CH/UNIT NAME, that you want to use in Project Plan tab here. You can edit it. |  |  |  |  | Yet to start | Milestone 0 | 0 | Yet to start | Creator | Milestone 0 | 0
Unit of Work | Role | Norms | Term | Class | Ch/Unit No | Ch/Unit Name | (In Progress) | Step A (In Progress) | Milestone 0 | 0 | Step A | Creator | Milestone 1 | 1
Chapter/Unit | Creator | 0.25 | 1 | Nursery | 1 | Chapter Name 1 | (Done) | Step A (Done) | Milestone 1 | 1 | Step B | Reviewer 1 | Milestone 1 | 1
Book | Reviewer 1 | 0.5 | 2 | LKG | 2 | Chapter Name 2 |  | Step B (In Progress) | Milestone 1 | 1 | Step C | Editor | Milestone 2 | 2
ASM | Reviewer 2 | 0.75 | 3 | SKG | 3 | Chapter Name 3 |  | Step B (Done) | Milestone 1 | 1 | Step D | Design | Milestone 2 | 2
SE | Reviewer 3 | 1 |  | Class 1 | 4 | Chapter Name 4 |  | Step C (In Progress) | Milestone 1 | 1 | Step E | Creator | Milestone 3 | 3
| Editor | 1.25 |  | Class 2 | 5 | Chapter Name 5 |  | Step C (Done) | Milestone 2 | 2 | Step F | DTP | Milestone 4 | 4
| Design | 1.5 |  | Class 3 | 6 | Chapter Name 6 |  | Step D (In Progress) | Milestone 2 | 2 | Step G | Reviewer 1 | Milestone 5 | 5
| AVC | 1.75 |  | Class 4 | 7 | Chapter Name 7 |  | Step D (Done) | Milestone 2 | 2 | Step H | DTP
| DTP | 2 |  | Class 5 | 8 | Chapter Name 8 |  | Step E (In Progress) | Milestone 2 | 2 | Step I | Reviewer 2
| Epub Vendor | 2.25 |  | Class 6 | 9 | Chapter Name 9 |  | Step E (Done) | Milestone 3 | 3
| QA | 2.5 |  | Class 7 | 10 | Chapter Name 10 |  | Step F (In Progress) | Milestone 3 | 3
| Freelancer | 2.75 |  | Class 8 | 11 | Chapter Name 11 |  | Step F (Done) | Milestone 4 | 4
|  | 3 |  | Class 9 | 12 | Chapter Name 12 |  | Step G (In Progress) | Milestone 4 | 4
|  | 3.25 |  | Class 10 | 13 | Chapter Name 13 |  | Step G (Done) | Milestone 5 | 5
|  | 3.5 |  | Class 11 | 14 | Chapter Name 14 |  | Step H (In Progress)
|  | 3.75 |  | Class 12 | 15 | Chapter Name 15 |  | Step H (Done)
|  | 4 |  |  | 16 | Chapter Name 16 |  | Step I (In Progress)
|  | 4.25 |  |  | 17 | Chapter Name 17 |  | Step I (Done)
|  | 4.5 |  |  | 18 | Chapter Name 18
|  | 4.75 |  |  | 19 | Chapter Name 19
|  | 5 |  |  | 20 | Chapter Name 20
|  | 5.25 |  |  | 21 | Chapter Name 21
|  | 5.5 |  |  | 22 | Chapter Name 22
|  | 5.75 |  |  | 23 | Chapter Name 23
|  | 6 |  |  | 24 | Chapter Name 24
|  | 6.25 |  |  | 25 | Chapter Name 25
|  | 6.5 |  |  | 26 | Chapter Name 26
|  | 6.75 |  |  | 27 | Chapter Name 27
|  | 7 |  |  | 28 | Chapter Name 28
|  | 7.25 |  |  | 29 | Chapter Name 29
|  | 7.5 |  |  | 30 | Chapter Name 30
|  | 7.75 |  |  |  | Chapter Name 31
|  | 8 |  |  |  | Chapter Name 32
|  | 8.25 |  |  |  | Chapter Name 33
|  | 8.5 |  |  |  | Chapter Name 34
|  | 8.75 |  |  |  | Chapter Name 35
|  | 9 |  |  |  | Chapter Name 36
|  | 9.25 |  |  |  | Chapter Name 37
|  | 9.5 |  |  |  | Chapter Name 38
|  | 9.75 |  |  |  | Chapter Name 39
|  | 10 |  |  |  | Chapter Name 40
Chapter Name 41
Chapter Name 42
Chapter Name 43
Chapter Name 44
Chapter Name 45
Chapter Name 46
Chapter Name 47
Chapter Name 48
Chapter Name 49
Chapter Name 50
Chapter Name 51
Chapter Name 52
Chapter Name 53
Chapter Name 54
Chapter Name 55
Chapter Name 56
Chapter Name 57
Chapter Name 58
Chapter Name 59
Chapter Name 60
Chapter Name 61
Chapter Name 62
Chapter Name 63
Chapter Name 64
Chapter Name 65
Chapter Name 66
Chapter Name 67
Chapter Name 68
Chapter Name 69
Chapter Name 70

## Steps+Norms
Steps | Step Details | Unit of Work | Role | Cluster 1 Norms | Cluster 2 Norms | Cluster 3 Norms | Buffer | Parallel Dependency
Step A | Definition of Step A | Chapter/Unit | Creator | 0.5 | 2 | 3
Step B | Definition of Step B | Chapter/Unit | Reviewer 1 | 0.5 | 0.5 | 0.5 |  | Step A
Step C | Definition of Step C | Chapter/Unit | Editor | 0.5 | 1.75 | 1.75 | 1 | Step B
Step D | Definition of Step D | Chapter/Unit | Design | 0.5 | 0.5 | 0.5 |  | Step A
Step E | Definition of Step E | Chapter/Unit | Creator | 0.5 | 0.5 | 0.5 |  | Step D
Step F | Definition of Step F | Book | DTP | 0.5 | 0.5 | 0.5 |  | Step E
Step G | Definition of Step G | Book | Reviewer 1 | 0.5 | 0.5 | 0.5 | 1 | Step F
Step H | Definition of Step H | Book | DTP | 0.5 | 0.5 | 0.5 |  | Step G
Step I | Definition of Step I | Book | Reviewer 2 | 0.5 | 0.5 | 0.5 |  | Step H

## Cluster Details
Cluster | Cluster Definition | Any other remarks
Cluster 1
Cluster 2
Cluster 3

## Team
Creation Bandwidth | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 5.5
Review Bandwidth | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 4
Name | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10
Holidays | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05
Holidays | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02 | 2025-10-02
Holidays
Holidays
Holidays
Leaves | 2025-09-15 | 2025-09-15 | 2025-09-16 | 2025-09-22
Leaves | 2025-09-16 | 2025-09-16
Leaves | 2025-09-17 | 2025-09-17
Leaves | 2025-09-18
Leaves | 2025-09-19
Leaves | 2025-09-20
Leaves | 2025-09-21
Leaves | 2025-09-22
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves
Leaves

## Bandwidth Plan
Chapter/Unit Level Bandwidth Analysis | [13 empty] | Book Level Bandwidth Analysis | [13 empty] | ASM Level Bandwidth Analysis | [13 empty] | SE Level Bandwidth Analysis
Role | Cluster 1 Effort | Total # Cluster 1 units | Cluster 2 Effort | Total # Cluster 2 units | Cluster 3 Effort | Total # Cluster 3 units | Total effort (man-days) | Resources bandwidth available | Start Date for the role | Expected end date (for each role) | Available working days | Resources required | Resoruce Surplus/Deficit | Role | Cluster 1 Effort | Total # Cluster 1 units | Cluster 2 Effort | Total # Cluster 2 units | Cluster 3 Effort | Total # Cluster 3 units | Total effort (man-days) | Resources available | Start Date | Expected end date | Available working days | Resources required | Resoruce Surplus/Deficit | Role | Cluster 1 Effort | Total # Cluster 1 units | Cluster 2 Effort | Total # Cluster 2 units | Cluster 3 Effort | Total # Cluster 3 units | Total effort (man-days) | Resources available | Start Date | Expected end date | Available working days | Resources required | Resoruce Surplus/Deficit | Role | Cluster 1 Effort | Total # Cluster 1 units | Cluster 2 Effort | Total # Cluster 2 units | Cluster 3 Effort | Total # Cluster 3 units | Total effort (man-days) | Resources available | Start Date | Expected end date | Available working days | Resources required | Resoruce Surplus/Deficit
Creator | 1 | 16 | 2.5 | 16 | 3.5 |  | 61.6 | 3 | 2025-07-02 | 2025-07-25 | 16.2 | 3.8025 | -0.80247 | Creator | 0 | 3 | 0 |  | 0 |  | 0 | 3 | 2025-07-02 | 2025-07-25 | 16.2 | 0 | 3 | Creator | 0 | 47 | 0 |  | 0 |  | 0 | 0.5 | 2026-03-16 | 2026-04-13 | 18.9 | 0 | 0.5 | Creator | 0 | 3 | 0 |  | 0 |  | 0 | 3 | 2025-07-02 | 2025-07-25 | 16.2 | 0 | 3
Reviewer 1 | 0.5 | 16 | 0.5 | 16 | 0.5 |  | 17.6 | 2 | 2025-07-07 | 2025-07-25 | 13.5 | 1.3037 | 0.6963 | Reviewer 1 | 0.5 | 3 | 0.5 |  | 0.5 |  | 1.65 | 2 | 2025-07-07 | 2025-07-25 | 13.5 | 0.12222 | 1.8778 | Reviewer 1 | 0 | 47 | 0 |  | 0 |  | 0 | 4 | 2025-07-07 | 2025-07-25 | 13.5 | 0 | 4 | Reviewer 1 | 0.5 | 3 | 0.5 |  | 0.5 |  | 1.65 | 2 | 2025-07-07 | 2025-07-25 | 13.5 | 0.12222 | 1.8778
Editor | 0.5 | 16 | 1.75 | 16 | 1.75 |  | 39.6 | 1 | 2025-07-09 | 2025-07-25 | 11.7 | 3.3846 | -2.3846 | Editor | 0 | 3 | 0 |  | 0 |  | 0 | 1 | 2025-07-09 | 2025-07-25 | 11.7 | 0 | 1 | Editor | 0 | 47 | 0 |  | 0 |  | 0 |  | 2025-07-09 | 2025-07-25 | 11.7 | 0 | 0 | Editor | 0 | 3 | 0 |  | 0 |  | 0 | 1 | 2025-07-09 | 2025-07-25 | 11.7 | 0 | 1
Design | 0.5 |  | 0.5 |  | 0.5 |  | 0 |  |  |  | 0 |  | 0 | Design | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | Design | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | Design | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
DTP | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | DTP | 1 |  | 1 |  | 1 |  | 0 |  |  |  | 0 |  | 0 | DTP | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | DTP | 1 |  | 1 |  | 1 |  | 0 |  |  |  | 0 |  | 0
Reviewer 2 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | Reviewer 2 | 0.5 |  | 0.5 |  | 0.5 |  | 0 |  |  |  | 0 |  | 0 | Reviewer 2 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | Reviewer 2 | 0.5 |  | 0.5 |  | 0.5 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
| 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0
Formulas:
Available working days = 0.9*NETWORKDAYS.INTL([Start Date for the role],[Expected end date (for each role)])
Available working days = 0.9*NETWORKDAYS.INTL([Start Date],[Expected end date])

## Sheet29
Are we delivering PROJECT TERM WISE OR IN FULL
How are creators working on this project? | Are all creators working on 1 grade together?
Different creators wokring on different grades
aRE WE DELIVERING IN TRANCHES
Delivery dates of DIFFERENT TRANCHES separately?
wHAT IS COVERED IN EACH TRANCHE FOR EACH GRADE
Will the same # of people work on different tranches? If not, how will it change?

## Project Plan
[12 empty] | Milestone 1 | Milestone 1 | Milestone 2 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Term | Class | Ch/Unit No | Ch/Unit Name | Cluster | Creator | Reviewer 1 | Reviewer 2 | Status | Milestone | Milestone# | Start Date | Step A | Step B | Step C | Step D | Step E | Step F | Step G | Step H | Step I
1 | Class 1 | 1 | Chapter Name 1 | Cluster 3 | Person 2 | Person 1 | Person 6 | Yet to start | Milestone 0 | 0 | 2025-08-04 | 2025-08-07 | 2025-08-08 | 2025-08-13 | 2025-08-08 | 2025-08-11 | 2025-08-12 | 2025-08-14 | 2025-08-15 | 2025-08-18
1 | Class 1 | 2 | Chapter Name 2 | Cluster 1 | Person 3 | Person 1 | Person 6 | Step F (Done) | Milestone 4 | 4 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-11 | 2025-08-07 | 2025-08-08 | 2025-08-11 | 2025-08-13 | 2025-08-14 | 2025-08-15
2 | Class 1 | 3 | Chapter Name 3 | Cluster 2 | Person 4 | Person 1 | Person 6 | Step C (In Progress) | Milestone 1 | 1 | 2025-08-06 | 2025-08-08 | 2025-08-11 | 2025-08-14 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-15 | 2025-08-18 | 2025-08-19
2 | Class 1 | 4 | Chapter Name 4 | Cluster 2 | Person 2 | Person 1 | Person 6 | Step D (In Progress) | Milestone 2 | 2 | 2025-08-07 | 2025-08-11 | 2025-08-12 | 2025-08-15 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-18 | 2025-08-19 | 2025-08-20
1 | Class 2 | 1 | Chapter Name 5 | Cluster 1 | Person 3 | Person 1 | Person 6 | Step C (In Progress) | Milestone 1 | 1 | 2025-08-08 | 2025-08-11 | 2025-08-12 | 2025-08-14 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-18 | 2025-08-19 | 2025-08-20
1 | Class 2 | 2 | Chapter Name 6 | Cluster 2 | Person 4 | Person 1 | Person 6 | Step A (In Progress) | Milestone 0 | 0 | 2025-08-11 | 2025-08-13 | 2025-08-14 | 2025-08-19 | 2025-08-14 | 2025-08-15 | 2025-08-18 | 2025-08-20 | 2025-08-21 | 2025-08-22
2 | Class 2 | 3 | Chapter Name 7 | Cluster 1 | Person 2 | Person 1 | Person 6 | Step B (In Progress) | Milestone 1 | 1 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-18 | 2025-08-14 | 2025-08-15 | 2025-08-18 | 2025-08-20 | 2025-08-21 | 2025-08-22
2 | Class 2 | 4 | Chapter Name 8 | Cluster 2 | Person 3 | Person 1 | Person 6 | Step A (In Progress) | Milestone 0 | 0 | 2025-08-13 | 2025-08-15 | 2025-08-18 | 2025-08-21 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-22 | 2025-08-25 | 2025-08-26
1 | Class 3 | 1 | Chapter Name 9 | Cluster 1 | Person 4 | Person 1 | Person 6 | Step A (In Progress) | Milestone 0 | 0 | 2025-08-14 | 2025-08-15 | 2025-08-18 | 2025-08-20 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-22 | 2025-08-25 | 2025-08-26
1 | Class 3 | 2 | Chapter Name 10 | Cluster 2 | Person 2 | Person 5 | Person 6 | Step D (Done) | Milestone 2 | 2 | 2025-08-15 | 2025-08-19 | 2025-08-20 | 2025-08-25 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-26 | 2025-08-27 | 2025-08-28
2 | Class 3 | 3 | Chapter Name 11 | Cluster 1 | Person 3 | Person 1 | Person 6 | Step C (In Progress) | Milestone 1 | 1 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-22 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-26 | 2025-08-27 | 2025-08-28
2 | Class 3 | 4 | Chapter Name 12 | Cluster 2 | Person 4 | Person 5 | Person 6 | Step B (In Progress) | Milestone 1 | 1 | 2025-08-19 | 2025-08-21 | 2025-08-22 | 2025-08-27 | 2025-08-22 | 2025-08-25 | 2025-08-26 | 2025-08-28 | 2025-08-29 | 2025-09-01
1 | Class 4 | 1 | Chapter Name 13 | Cluster 1 | Person 2 | Person 1 | Person 6 | Yet to start | Milestone 0 | 0 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-26 | 2025-08-22 | 2025-08-25 | 2025-08-26 | 2025-08-28 | 2025-08-29 | 2025-09-01
1 | Class 4 | 2 | Chapter Name 14 | Cluster 2 | Person 3 | Person 5 | Person 6 | Step F (Done) | Milestone 4 | 4 | 2025-08-21 | 2025-08-25 | 2025-08-26 | 2025-08-29 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-09-01 | 2025-09-02 | 2025-09-03
2 | Class 4 | 3 | Chapter Name 15 | Cluster 1 | Person 4 | Person 1 | Person 6 | Step C (In Progress) | Milestone 1 | 1 | 2025-08-22 | 2025-08-25 | 2025-08-26 | 2025-08-28 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-09-01 | 2025-09-02 | 2025-09-03
2 | Class 4 | 4 | Chapter Name 16 | Cluster 2 | Person 2 | Person 5 | Person 6 | Step D (In Progress) | Milestone 2 | 2 | 2025-08-25 | 2025-08-27 | 2025-08-28 | 2025-09-02 | 2025-08-28 | 2025-08-29 | 2025-09-01 | 2025-09-03 | 2025-09-04 | 2025-09-08
1 | Class 5 | 1 | Chapter Name 17 | Cluster 1 | Person 3 | Person 1 | Person 6 | Step C (In Progress) | Milestone 1 | 1 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-09-01 | 2025-08-28 | 2025-08-29 | 2025-09-01 | 2025-09-03 | 2025-09-04 | 2025-09-08
1 | Class 5 | 2 | Chapter Name 18 | Cluster 2 | Person 4 | Person 5 | Person 6 | Step A (In Progress) | Milestone 0 | 0 | 2025-08-27 | 2025-08-29 | 2025-09-01 | 2025-09-04 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-08 | 2025-09-09 | 2025-09-10
2 | Class 5 | 3 | Chapter Name 19 | Cluster 1 | Person 2 | Person 1 | Person 6 | Step B (In Progress) | Milestone 1 | 1 | 2025-08-28 | 2025-08-29 | 2025-09-01 | 2025-09-03 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-08 | 2025-09-09 | 2025-09-10
2 | Class 5 | 4 | Chapter Name 20 | Cluster 2 | Person 3 | Person 5 | Person 6 | Step A (In Progress) | Milestone 0 | 0 | 2025-08-29 | 2025-09-02 | 2025-09-03 | 2025-09-09 | 2025-09-03 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-12
1 | Class 6 | 1 | Chapter Name 21 | Cluster 1 | Person 4 | Person 1 | Person 6 | Step A (In Progress) | Milestone 0 | 0 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-08 | 2025-09-03 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-12
1 | Class 6 | 2 | Chapter Name 22 | Cluster 2 | Person 2 | Person 5 | Person 6 | Step D (Done) | Milestone 2 | 2 | 2025-09-02 | 2025-09-04 | 2025-09-08 | 2025-09-11 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-15 | 2025-09-16
2 | Class 6 | 3 | Chapter Name 23 | Cluster 1 | Person 3 | Person 1 | Person 6 | Step C (In Progress) | Milestone 1 | 1 | 2025-09-03 | 2025-09-04 | 2025-09-08 | 2025-09-10 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-15 | 2025-09-16
2 | Class 6 | 4 | Chapter Name 24 | Cluster 2 | Person 4 | Person 5 | Person 6 | Step B (In Progress) | Milestone 1 | 1 | 2025-09-04 | 2025-09-09 | 2025-09-10 | 2025-09-15 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-16 | 2025-09-17 | 2025-09-18
1 | Class 7 | 1 | Chapter Name 25 | Cluster 1 | Person 2 | Person 1 | Person 6 | Yet to start | Milestone 0 | 0 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-11 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-23 | 2025-09-24 | 2025-09-25
1 | Class 7 | 2 | Chapter Name 26 | Cluster 2 | Person 3 | Person 5 | Person 6 | Step F (Done) | Milestone 4 | 4 | 2025-09-08 | 2025-09-10 | 2025-09-11 | 2025-09-16 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-19
2 | Class 7 | 3 | Chapter Name 27 | Cluster 1 | Person 4 | Person 1 | Person 6 | Step C (In Progress) | Milestone 1 | 1 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-15 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-24 | 2025-09-25 | 2025-09-26
2 | Class 7 | 4 | Chapter Name 28 | Cluster 2 | Person 2 | Person 5 | Person 6 | Step D (In Progress) | Milestone 2 | 2 | 2025-09-10 | 2025-09-12 | 2025-09-15 | 2025-09-18 | 2025-09-15 | 2025-09-18 | 2025-09-19 | 2025-09-23 | 2025-09-24 | 2025-09-25
1 | Class 8 | 1 | Chapter Name 29 | Cluster 1 | Person 3 | Person 1 | Person 6 | Step C (In Progress) | Milestone 1 | 1 | 2025-09-11 | 2025-09-12 | 2025-09-23 | 2025-09-25 | 2025-09-15 | 2025-09-17 | 2025-09-18 | 2025-09-24 | 2025-09-25 | 2025-09-26
1 | Class 8 | 2 | Chapter Name 30 | Cluster 2 | Person 4 | Person 5 | Person 6 | Step A (In Progress) | Milestone 0 | 0 | 2025-09-12 | 2025-09-16 | 2025-09-17 | 2025-09-22 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-23 | 2025-09-24 | 2025-09-25
2 | Class 8 | 3 | Chapter Name 31 | Cluster 1 | Person 2 | Person 1 | Person 6 | Step B (In Progress) | Milestone 1 | 1 | 2025-09-15 | 2025-09-18 | 2025-09-23 | 2025-09-25 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-25 | 2025-09-26 | 2025-09-29
2 | Class 8 | 4 | Chapter Name 32 | Cluster 2 | Person 3 | Person 5 | Person 6 | Step A (In Progress) | Milestone 0 | 0 | 2025-09-16 | 2025-09-18 | 2025-09-19 | 2025-09-24 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-25 | 2025-09-26 | 2025-09-29

## Workload Tracker
Person / Date | time axis 2025-09-03 to 2026-02-10
Person 1 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 2 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 3 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 4 | 0.5 | 0 | 2 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Person 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Flat Task Log (Helper Sheet)
Chapter Name | Step | Cluster | Unit of work | Creator | Reviewer 1 | Reviewer 2 | Role | Allocation | Start Date | Step End Date | Workload
Chapter Name 1 | Step A | Cluster 3 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-05 | 2025-08-07 | 2
Chapter Name 1 | Step B | Cluster 3 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-07 | 2025-08-08 | 0.5
Chapter Name 1 | Step C | Cluster 3 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Editor |  | 2025-08-11 | 2025-08-13 | 1.75
Chapter Name 1 | Step D | Cluster 3 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Design |  | 2025-08-07 | 2025-08-08 | 0.5
Chapter Name 1 | Step E | Cluster 3 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-08 | 2025-08-11 | 0.5
Chapter Name 1 | Step F | Cluster 3 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-08-11 | 2025-08-12 | 0.5
Chapter Name 1 | Step G | Cluster 3 | Book | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 1 | Step H | Cluster 3 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-08-14 | 2025-08-15 | 0.5
Chapter Name 1 | Step I | Cluster 3 | Book | Person 2 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 2 | Step A | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-05 | 2025-08-06 | 0.5
Chapter Name 2 | Step B | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-06 | 2025-08-07 | 0.5
Chapter Name 2 | Step C | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Editor |  | 2025-08-08 | 2025-08-11 | 0.5
Chapter Name 2 | Step D | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Design |  | 2025-08-06 | 2025-08-07 | 0.5
Chapter Name 2 | Step E | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-07 | 2025-08-08 | 0.5
Chapter Name 2 | Step F | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-08 | 2025-08-11 | 0.5
Chapter Name 2 | Step G | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-12 | 2025-08-13 | 0.5
Chapter Name 2 | Step H | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 2 | Step I | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-14 | 2025-08-15 | 0.5
Chapter Name 3 | Step A | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-08-06 | 2025-08-08 | 2
Chapter Name 3 | Step B | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-08 | 2025-08-11 | 0.5
Chapter Name 3 | Step C | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Editor |  | 2025-08-12 | 2025-08-14 | 1.75
Chapter Name 3 | Step D | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Design |  | 2025-08-08 | 2025-08-11 | 0.5
Chapter Name 3 | Step E | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-08-11 | 2025-08-12 | 0.5
Chapter Name 3 | Step F | Cluster 2 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-08-12 | 2025-08-13 | 0.5
Chapter Name 3 | Step G | Cluster 2 | Book | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-14 | 2025-08-15 | 0.5
Chapter Name 3 | Step H | Cluster 2 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 3 | Step I | Cluster 2 | Book | Person 4 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-18 | 2025-08-19 | 0.5
Chapter Name 4 | Step A | Cluster 2 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-07 | 2025-08-11 | 2
Chapter Name 4 | Step B | Cluster 2 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-11 | 2025-08-12 | 0.5
Chapter Name 4 | Step C | Cluster 2 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Editor |  | 2025-08-13 | 2025-08-15 | 1.75
Chapter Name 4 | Step D | Cluster 2 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Design |  | 2025-08-11 | 2025-08-12 | 0.5
Chapter Name 4 | Step E | Cluster 2 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-12 | 2025-08-13 | 0.5
Chapter Name 4 | Step F | Cluster 2 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 4 | Step G | Cluster 2 | Book | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 4 | Step H | Cluster 2 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-08-18 | 2025-08-19 | 0.5
Chapter Name 4 | Step I | Cluster 2 | Book | Person 2 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 5 | Step A | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-08 | 2025-08-11 | 0.5
Chapter Name 5 | Step B | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-11 | 2025-08-12 | 0.5
Chapter Name 5 | Step C | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Editor |  | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 5 | Step D | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Design |  | 2025-08-11 | 2025-08-12 | 0.5
Chapter Name 5 | Step E | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-12 | 2025-08-13 | 0.5
Chapter Name 5 | Step F | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 5 | Step G | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 5 | Step H | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-18 | 2025-08-19 | 0.5
Chapter Name 5 | Step I | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 6 | Step A | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-08-11 | 2025-08-13 | 2
Chapter Name 6 | Step B | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 6 | Step C | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Editor |  | 2025-08-15 | 2025-08-19 | 1.75
Chapter Name 6 | Step D | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Design |  | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 6 | Step E | Cluster 2 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-08-14 | 2025-08-15 | 0.5
Chapter Name 6 | Step F | Cluster 2 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 6 | Step G | Cluster 2 | Book | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 6 | Step H | Cluster 2 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-08-20 | 2025-08-21 | 0.5
Chapter Name 6 | Step I | Cluster 2 | Book | Person 4 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 7 | Step A | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-12 | 2025-08-13 | 0.5
Chapter Name 7 | Step B | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 7 | Step C | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Editor |  | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 7 | Step D | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Design |  | 2025-08-13 | 2025-08-14 | 0.5
Chapter Name 7 | Step E | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-14 | 2025-08-15 | 0.5
Chapter Name 7 | Step F | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 7 | Step G | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 7 | Step H | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-08-20 | 2025-08-21 | 0.5
Chapter Name 7 | Step I | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 8 | Step A | Cluster 2 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-13 | 2025-08-15 | 2
Chapter Name 8 | Step B | Cluster 2 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 8 | Step C | Cluster 2 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Editor |  | 2025-08-19 | 2025-08-21 | 1.75
Chapter Name 8 | Step D | Cluster 2 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Design |  | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 8 | Step E | Cluster 2 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-18 | 2025-08-19 | 0.5
Chapter Name 8 | Step F | Cluster 2 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 8 | Step G | Cluster 2 | Book | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 8 | Step H | Cluster 2 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-22 | 2025-08-25 | 0.5
Chapter Name 8 | Step I | Cluster 2 | Book | Person 3 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 9 | Step A | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-08-14 | 2025-08-15 | 0.5
Chapter Name 9 | Step B | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 9 | Step C | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Editor |  | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 9 | Step D | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Design |  | 2025-08-15 | 2025-08-18 | 0.5
Chapter Name 9 | Step E | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-08-18 | 2025-08-19 | 0.5
Chapter Name 9 | Step F | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 9 | Step G | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 9 | Step H | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-08-22 | 2025-08-25 | 0.5
Chapter Name 9 | Step I | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 10 | Step A | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Creator | Person 2 | 2025-08-15 | 2025-08-19 | 2
Chapter Name 10 | Step B | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 10 | Step C | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Editor |  | 2025-08-21 | 2025-08-25 | 1.75
Chapter Name 10 | Step D | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Design |  | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 10 | Step E | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Creator | Person 2 | 2025-08-20 | 2025-08-21 | 0.5
Chapter Name 10 | Step F | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | DTP |  | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 10 | Step G | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 10 | Step H | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | DTP |  | 2025-08-26 | 2025-08-27 | 0.5
Chapter Name 10 | Step I | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 11 | Step A | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-18 | 2025-08-19 | 0.5
Chapter Name 11 | Step B | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 11 | Step C | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Editor |  | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 11 | Step D | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Design |  | 2025-08-19 | 2025-08-20 | 0.5
Chapter Name 11 | Step E | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-20 | 2025-08-21 | 0.5
Chapter Name 11 | Step F | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 11 | Step G | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 11 | Step H | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-26 | 2025-08-27 | 0.5
Chapter Name 11 | Step I | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 12 | Step A | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Creator | Person 4 | 2025-08-19 | 2025-08-21 | 2
Chapter Name 12 | Step B | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 12 | Step C | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Editor |  | 2025-08-25 | 2025-08-27 | 1.75
Chapter Name 12 | Step D | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Design |  | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 12 | Step E | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Creator | Person 4 | 2025-08-22 | 2025-08-25 | 0.5
Chapter Name 12 | Step F | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | DTP |  | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 12 | Step G | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 12 | Step H | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | DTP |  | 2025-08-28 | 2025-08-29 | 0.5
Chapter Name 12 | Step I | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 13 | Step A | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-20 | 2025-08-21 | 0.5
Chapter Name 13 | Step B | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 13 | Step C | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Editor |  | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 13 | Step D | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Design |  | 2025-08-21 | 2025-08-22 | 0.5
Chapter Name 13 | Step E | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-22 | 2025-08-25 | 0.5
Chapter Name 13 | Step F | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 13 | Step G | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 13 | Step H | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-08-28 | 2025-08-29 | 0.5
Chapter Name 13 | Step I | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 14 | Step A | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Creator | Person 3 | 2025-08-21 | 2025-08-25 | 2
Chapter Name 14 | Step B | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 14 | Step C | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Editor |  | 2025-08-27 | 2025-08-29 | 1.75
Chapter Name 14 | Step D | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Design |  | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 14 | Step E | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Creator | Person 3 | 2025-08-26 | 2025-08-27 | 0.5
Chapter Name 14 | Step F | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | DTP |  | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 14 | Step G | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 14 | Step H | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | DTP |  | 2025-09-01 | 2025-09-02 | 0.5
Chapter Name 14 | Step I | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 15 | Step A | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-08-22 | 2025-08-25 | 0.5
Chapter Name 15 | Step B | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 15 | Step C | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Editor |  | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 15 | Step D | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Design |  | 2025-08-25 | 2025-08-26 | 0.5
Chapter Name 15 | Step E | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-08-26 | 2025-08-27 | 0.5
Chapter Name 15 | Step F | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 15 | Step G | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 15 | Step H | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-09-01 | 2025-09-02 | 0.5
Chapter Name 15 | Step I | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 16 | Step A | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Creator | Person 2 | 2025-08-25 | 2025-08-27 | 2
Chapter Name 16 | Step B | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 16 | Step C | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Editor |  | 2025-08-29 | 2025-09-02 | 1.75
Chapter Name 16 | Step D | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Design |  | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 16 | Step E | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Creator | Person 2 | 2025-08-28 | 2025-08-29 | 0.5
Chapter Name 16 | Step F | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | DTP |  | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 16 | Step G | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 16 | Step H | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | DTP |  | 2025-09-03 | 2025-09-04 | 0.5
Chapter Name 16 | Step I | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 17 | Step A | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-26 | 2025-08-27 | 0.5
Chapter Name 17 | Step B | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 17 | Step C | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Editor |  | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 17 | Step D | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Design |  | 2025-08-27 | 2025-08-28 | 0.5
Chapter Name 17 | Step E | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-08-28 | 2025-08-29 | 0.5
Chapter Name 17 | Step F | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 17 | Step G | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 17 | Step H | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-09-03 | 2025-09-04 | 0.5
Chapter Name 17 | Step I | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 18 | Step A | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Creator | Person 4 | 2025-08-27 | 2025-08-29 | 2
Chapter Name 18 | Step B | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 18 | Step C | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Editor |  | 2025-09-02 | 2025-09-04 | 1.75
Chapter Name 18 | Step D | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Design |  | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 18 | Step E | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Creator | Person 4 | 2025-09-01 | 2025-09-02 | 0.5
Chapter Name 18 | Step F | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | DTP |  | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 18 | Step G | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 18 | Step H | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | DTP |  | 2025-09-08 | 2025-09-09 | 0.5
Chapter Name 18 | Step I | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 19 | Step A | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-08-28 | 2025-08-29 | 0.5
Chapter Name 19 | Step B | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 19 | Step C | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Editor |  | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 19 | Step D | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Design |  | 2025-08-29 | 2025-09-01 | 0.5
Chapter Name 19 | Step E | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-09-01 | 2025-09-02 | 0.5
Chapter Name 19 | Step F | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 19 | Step G | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 19 | Step H | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-09-08 | 2025-09-09 | 0.5
Chapter Name 19 | Step I | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 20 | Step A | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Creator | Person 3 | 2025-08-29 | 2025-09-02 | 2
Chapter Name 20 | Step B | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 20 | Step C | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Editor |  | 2025-09-05 | 2025-09-09 | 1.75
Chapter Name 20 | Step D | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Design |  | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 20 | Step E | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Creator | Person 3 | 2025-09-03 | 2025-09-04 | 0.5
Chapter Name 20 | Step F | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | DTP |  | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 20 | Step G | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 20 | Step H | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | DTP |  | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 20 | Step I | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-11 | 2025-09-12 | 0.5
Chapter Name 21 | Step A | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-09-01 | 2025-09-02 | 0.5
Chapter Name 21 | Step B | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 21 | Step C | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Editor |  | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 21 | Step D | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Design |  | 2025-09-02 | 2025-09-03 | 0.5
Chapter Name 21 | Step E | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-09-03 | 2025-09-04 | 0.5
Chapter Name 21 | Step F | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 21 | Step G | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 21 | Step H | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 21 | Step I | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-11 | 2025-09-12 | 0.5
Chapter Name 22 | Step A | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Creator | Person 2 | 2025-09-02 | 2025-09-04 | 2
Chapter Name 22 | Step B | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 22 | Step C | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Editor |  | 2025-09-09 | 2025-09-11 | 1.75
Chapter Name 22 | Step D | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Design |  | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 22 | Step E | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Creator | Person 2 | 2025-09-08 | 2025-09-09 | 0.5
Chapter Name 22 | Step F | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | DTP |  | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 22 | Step G | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-11 | 2025-09-12 | 0.5
Chapter Name 22 | Step H | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | DTP |  | 2025-09-12 | 2025-09-15 | 0.5
Chapter Name 22 | Step I | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-15 | 2025-09-16 | 0.5
Chapter Name 23 | Step A | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-09-03 | 2025-09-04 | 0.5
Chapter Name 23 | Step B | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 23 | Step C | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Editor |  | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 23 | Step D | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Design |  | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 23 | Step E | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-09-08 | 2025-09-09 | 0.5
Chapter Name 23 | Step F | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 23 | Step G | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-11 | 2025-09-12 | 0.5
Chapter Name 23 | Step H | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-09-12 | 2025-09-15 | 0.5
Chapter Name 23 | Step I | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-15 | 2025-09-16 | 0.5
Chapter Name 24 | Step A | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Creator | Person 4 | 2025-09-05 | 2025-09-09 | 2
Chapter Name 24 | Step B | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 24 | Step C | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Editor |  | 2025-09-11 | 2025-09-15 | 1.75
Chapter Name 24 | Step D | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Design |  | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 24 | Step E | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Creator | Person 4 | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 24 | Step F | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | DTP |  | 2025-09-11 | 2025-09-12 | 0.5
Chapter Name 24 | Step G | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-15 | 2025-09-16 | 0.5
Chapter Name 24 | Step H | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | DTP |  | 2025-09-16 | 2025-09-17 | 0.5
Chapter Name 24 | Step I | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-17 | 2025-09-18 | 0.5
Chapter Name 25 | Step A | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-09-05 | 2025-09-08 | 0.5
Chapter Name 25 | Step B | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-08 | 2025-09-09 | 0.5
Chapter Name 25 | Step C | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Editor |  | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 25 | Step D | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Design |  | 2025-09-08 | 2025-09-09 | 0.5
Chapter Name 25 | Step E | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 25 | Step F | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 25 | Step G | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-22 | 2025-09-23 | 0.5
Chapter Name 25 | Step H | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-09-23 | 2025-09-24 | 0.5
Chapter Name 25 | Step I | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 26 | Step A | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Creator | Person 3 | 2025-09-08 | 2025-09-10 | 2
Chapter Name 26 | Step B | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 26 | Step C | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Editor |  | 2025-09-12 | 2025-09-16 | 1.75
Chapter Name 26 | Step D | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Design |  | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 26 | Step E | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Creator | Person 3 | 2025-09-11 | 2025-09-12 | 0.5
Chapter Name 26 | Step F | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | DTP |  | 2025-09-12 | 2025-09-15 | 0.5
Chapter Name 26 | Step G | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-16 | 2025-09-17 | 0.5
Chapter Name 26 | Step H | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | DTP |  | 2025-09-17 | 2025-09-18 | 0.5
Chapter Name 26 | Step I | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-18 | 2025-09-19 | 0.5
Chapter Name 27 | Step A | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-09-09 | 2025-09-10 | 0.5
Chapter Name 27 | Step B | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 27 | Step C | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Editor |  | 2025-09-12 | 2025-09-15 | 0.5
Chapter Name 27 | Step D | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Design |  | 2025-09-10 | 2025-09-11 | 0.5
Chapter Name 27 | Step E | Cluster 1 | Chapter/Unit | Person 4 | Person 1 | Person 6 | Creator | Person 4 | 2025-09-11 | 2025-09-12 | 0.5
Chapter Name 27 | Step F | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-09-12 | 2025-09-15 | 0.5
Chapter Name 27 | Step G | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-23 | 2025-09-24 | 0.5
Chapter Name 27 | Step H | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | DTP |  | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 27 | Step I | Cluster 1 | Book | Person 4 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-25 | 2025-09-26 | 0.5
Chapter Name 28 | Step A | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Creator | Person 2 | 2025-09-10 | 2025-09-12 | 2
Chapter Name 28 | Step B | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-12 | 2025-09-15 | 0.5
Chapter Name 28 | Step C | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Editor |  | 2025-09-16 | 2025-09-18 | 1.75
Chapter Name 28 | Step D | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Design |  | 2025-09-12 | 2025-09-15 | 0.5
Chapter Name 28 | Step E | Cluster 2 | Chapter/Unit | Person 2 | Person 5 | Person 6 | Creator | Person 2 | 2025-09-17 | 2025-09-18 | 0.5
Chapter Name 28 | Step F | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | DTP |  | 2025-09-18 | 2025-09-19 | 0.5
Chapter Name 28 | Step G | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-22 | 2025-09-23 | 0.5
Chapter Name 28 | Step H | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | DTP |  | 2025-09-23 | 2025-09-24 | 0.5
Chapter Name 28 | Step I | Cluster 2 | Book | Person 2 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 29 | Step A | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-09-11 | 2025-09-12 | 0.5
Chapter Name 29 | Step B | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-22 | 2025-09-23 | 0.5
Chapter Name 29 | Step C | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Editor |  | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 29 | Step D | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Design |  | 2025-09-12 | 2025-09-15 | 0.5
Chapter Name 29 | Step E | Cluster 1 | Chapter/Unit | Person 3 | Person 1 | Person 6 | Creator | Person 3 | 2025-09-16 | 2025-09-17 | 0.5
Chapter Name 29 | Step F | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-09-17 | 2025-09-18 | 0.5
Chapter Name 29 | Step G | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-23 | 2025-09-24 | 0.5
Chapter Name 29 | Step H | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | DTP |  | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 29 | Step I | Cluster 1 | Book | Person 3 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-25 | 2025-09-26 | 0.5
Chapter Name 30 | Step A | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Creator | Person 4 | 2025-09-12 | 2025-09-16 | 2
Chapter Name 30 | Step B | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-16 | 2025-09-17 | 0.5
Chapter Name 30 | Step C | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Editor |  | 2025-09-18 | 2025-09-22 | 1.75
Chapter Name 30 | Step D | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Design |  | 2025-09-16 | 2025-09-17 | 0.5
Chapter Name 30 | Step E | Cluster 2 | Chapter/Unit | Person 4 | Person 5 | Person 6 | Creator | Person 4 | 2025-09-17 | 2025-09-18 | 0.5
Chapter Name 30 | Step F | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | DTP |  | 2025-09-18 | 2025-09-19 | 0.5
Chapter Name 30 | Step G | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-22 | 2025-09-23 | 0.5
Chapter Name 30 | Step H | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | DTP |  | 2025-09-23 | 2025-09-24 | 0.5
Chapter Name 30 | Step I | Cluster 2 | Book | Person 4 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 31 | Step A | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-09-17 | 2025-09-18 | 0.5
Chapter Name 31 | Step B | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-22 | 2025-09-23 | 0.5
Chapter Name 31 | Step C | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Editor |  | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 31 | Step D | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Design |  | 2025-09-18 | 2025-09-19 | 0.5
Chapter Name 31 | Step E | Cluster 1 | Chapter/Unit | Person 2 | Person 1 | Person 6 | Creator | Person 2 | 2025-09-19 | 2025-09-22 | 0.5
Chapter Name 31 | Step F | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-09-22 | 2025-09-23 | 0.5
Chapter Name 31 | Step G | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 1 | Person 1 | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 31 | Step H | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | DTP |  | 2025-09-25 | 2025-09-26 | 0.5
Chapter Name 31 | Step I | Cluster 1 | Book | Person 2 | Person 1 | Person 6 | Reviewer 2 | Person 6 | 2025-09-26 | 2025-09-29 | 0.5
Chapter Name 32 | Step A | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Creator | Person 3 | 2025-09-16 | 2025-09-18 | 2
Chapter Name 32 | Step B | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-18 | 2025-09-19 | 0.5
Chapter Name 32 | Step C | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Editor |  | 2025-09-22 | 2025-09-24 | 1.75
Chapter Name 32 | Step D | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Design |  | 2025-09-18 | 2025-09-19 | 0.5
Chapter Name 32 | Step E | Cluster 2 | Chapter/Unit | Person 3 | Person 5 | Person 6 | Creator | Person 3 | 2025-09-19 | 2025-09-22 | 0.5
Chapter Name 32 | Step F | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | DTP |  | 2025-09-22 | 2025-09-23 | 0.5
Chapter Name 32 | Step G | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | Reviewer 1 | Person 5 | 2025-09-24 | 2025-09-25 | 0.5
Chapter Name 32 | Step H | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | DTP |  | 2025-09-25 | 2025-09-26 | 0.5
Chapter Name 32 | Step I | Cluster 2 | Book | Person 3 | Person 5 | Person 6 | Reviewer 2 | Person 6 | 2025-09-26 | 2025-09-29 | 0.5
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Start Date = IFERROR(WORKDAY([Step End Date],ROUND(-[Workload],0)),"")
Step End Date = IFERROR(INDEX('Project Plan'!$D2:FZ1813,MATCH([Chapter Name],'Project Plan'!$D2:D1813,0),MATCH([Step],'Project Plan'!$D2:FZ2,0)),"")

## Dashboard_Config
SIMPLE DASHBOARD CONFIG
PROJECT_SHEET | Project Plan
CLASS_COLUMN | Class
CHAPTER_COLUMN | Ch/Unit No
MILESTONE_COLUMN | Milestone
STATUS_COLUMN | Status
STEP_START_COLUMN | 12
VALIDATIONS_SHEET | Validations

## Enhanced Dashboard
📊 ENHANCED PROJECT DASHBOARD
Last Updated: 3/12/2026, 4:18:03 PM | [10 empty] | FALSE | 🔄 Check to Refresh
Total Units |  |  | Total Classes |  |  | Completion % |  |  | Projected End
32 |  |  | 8 |  |  | 34.9% |  |  | 2026-03-12
Class 1 End |  |  | Class 2 End |  |  | Class 3 End |  |  | Class 4 End
2026-03-12 |  |  | 2026-03-12 |  |  | 2026-03-12 |  |  | 2026-03-12
Class 5 End |  |  | Class 6 End |  |  | Class 7 End |  |  | Class 8 End
2026-03-12 |  |  | 2026-03-12 |  |  | 2026-03-12 |  |  | 2026-03-12
📅 WEEKLY PLANNED VS ACHIEVED (4 Aug 2025 → 29 Sept 2025)
Milestone | Till Date Plan | Till Date Actual | 4 Aug - 10 Aug |  | 11 Aug - 17 Aug |  | 18 Aug - 24 Aug |  | 25 Aug - 31 Aug |  | 1 Sept - 7 Sept |  | 8 Sept - 14 Sept |  | 15 Sept - 21 Sept |  | 22 Sept - 28 Sept |  | 29 Sept - 5 Oct
Milestone | Plan | Actual | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A | P | A
Milestone 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 1 | 32 | 21 | 3 | 2 | 6 | 3 | 4 | 3 | 6 | 5 | 4 | 2 | 6 | 5 | 3 | 1 | 0 | 0 | 0 | 0
Milestone 2 | 32 | 8 | 0 | 0 | 5 | 2 | 5 | 0 | 5 | 2 | 4 | 1 | 5 | 1 | 4 | 2 | 4 | 0 | 0 | 0
Milestone 3 | 32 | 3 | 1 | 1 | 6 | 0 | 4 | 0 | 6 | 1 | 4 | 0 | 6 | 1 | 3 | 0 | 2 | 0 | 0 | 0
Milestone 4 | 32 | 3 | 0 | 0 | 5 | 1 | 6 | 0 | 4 | 1 | 4 | 0 | 6 | 0 | 5 | 1 | 2 | 0 | 0 | 0
Milestone 5 | 32 | 0 | 0 | 0 | 3 | 0 | 6 | 0 | 4 | 0 | 4 | 0 | 6 | 0 | 2 | 0 | 7 | 0 | 0 | 0
📋 MILESTONE-CLASS MATRIX
Milestone | Class 1 | Class 2 | Class 3 | Class 4 | Class 5 | Class 6 | Class 7 | Class 8
Yet to Start | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 0 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2
Milestone 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 2
Milestone 2 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0
Milestone 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Milestone 4 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0
Milestone 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
⚠️ RISK SUMMARY
Risk Level | Class 1: Count; Class 2: Description
High Risk | Class 1: 320; Class 2: Over 7 days overdue
Medium Risk | Class 1: 0; Class 2: 3-7 days overdue
Low Risk | Class 1: 0; Class 2: 1-3 days overdue

## Helper (hidden)
Step A | (In Progress) | Step A(In Progress)
Step B | (Done) | Step A(Done)
Step C |  | Step B(In Progress)
Step D |  | Step B(Done)
Step E |  | Step C(In Progress)
Step F |  | Step C(Done)
Step G |  | Step D(In Progress)
Step H |  | Step D(Done)
Step I |  | Step E(In Progress)
Step E(Done)
Step F(In Progress)
Step F(Done)
Step G(In Progress)
Step G(Done)
Step H(In Progress)
Step H(Done)
Step I(In Progress)
Step I(Done)