## Scope and Volume
Product | Sub-product | Total Estimated Count
Print | Print Book | 100 books
Digital | MP4 (Simpler ones) | 1000 assets
| MP4s (Tricky ones) | 170 assets
| HTML | 4423 assets
| Digital PDFs | 5687 assets
| Epubs | 65 Epubs
CTRBs |  | 76 CTRBs
Renewal of Text Licenses

## Budget Summary View
All values in INR
Avg Salary per month | 70000 | 70000 | 70000 | 55000 | 45000 | 45000 | 200000 | 80000
Elements of Product | DTP | QA | Design | IR | DTP Vendor/FL | Design Vendor/FL | Tech Team | PM | Total Required Budget in INR | Term 1 + 2 | # Resources requried | [9 empty] | Role | March | April | May | June | July | August | September | October | November | December | January | February
Print | 158333.3333 | 50000 | 0 | 0 | 107142.8571 | 0 | 0 | 0 | 315476.1905 | Delivery Type | Start Date | End Date | Total Available Working Days | Available Working days for Term 1 | #Creators' mandays required | #R1s mandays' required | #R2s mandays required | Creator | Reviewer 1 | Reviewer 2 | Creator | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Digital | 52916.6667 | 162500 | 0 | 144800.5952 | 0 | 160714.2857 | 54166.6667 | 0 | 575098.2143 | Print | 2026-03-20 | 2026-11-01 | 120.75 | 120.75 | 211250 | 212500 | 0 | 1749.4824 | 1759.8344 | 0 | Reviewer 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
CTRBs | 28500 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 38000
PM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57142.8571 | 57142.8571 | Digital | 2026-12-01 | 2027-03-15 | 56.25 | 56.25 | 0 | 0 | 0 | 0 | 0 | 0 | Reviewer 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total | 239750 | 222000 |  | 144800.5952 | 107142.8571 | 160714.2857 | 54166.6667 | 57142.8571 | 985717.2619
Print - 1 Dec Digital - 31th March 27
Plan for 1-1-3
Keep 1-2-3 (ASM & Shikhar)

## Norms (hidden)
Steps | Unit of calculation | Unit of Norms | DTP | QA | Design | IR | DTP Vendor/FL | Design Vendor/FL | Tech Team | PM
Print
Book (Print Asset) - Identify negative credits & images | Book | Hours | 0.5 | 0 | 0 |  | 0 | 0 |  | 0
Book (Print Asset) - Rebranding of book (covers & initial pages) | Book | Hours | 1 | 0 | 0 |  | 2 | 0 |  | 0
QA | Book | Hours |  | 0.5
QA CI | Book | Hours | 0.66667 |  |  |  | 1.3333
QA CIC and Sign-off | Book | Hours |  | 0.5
Ripping Approvals | Book | Hours | 1
Digital
MP4s (Digital Asset) - Rebranding of videos (Simpler Ones) | Asset | Hours | [5 empty] | 0.5
MP4s (Digital Asset) - Rebranding of videos (Tricky Ones) | Asset | Hours
PDFs (Digital Asset) - Rebranding of PDFs | Asset | Hours | 0.016667
HTMLs (Digital Asset) - Rebranding of HTMLs | Asset | Hours |  |  |  | 0.083333
Update the Epub | Book | Hours | 0.16667 | 1 |  |  |  |  | 0.41667
QA of Epub and Sign-off | Book | Hours |  | 4 |  |  |  |  | 0.16667
CTRBs
Rebranding CTRBs | CTRB | Hours | 0.5
QA and Sign-off | CTRB | Hours | 0.25 | 0.25
Project Management | Book | Hours | [7 empty] | 1
[11 empty] | Creator | 3 | Reviewer | 2
[12 empty] | 1.5 |  | 1
0.5
0.25
1

## Budget (Estimated)
Cost per role per month
|  | (Norms per unit in mandays) | [9 empty] | (Total # required mandays) | [7 empty] | 70000 | 70000 | 70000 | 55000 | 45000 | 45000 | 200000 | 80000 | 985717.2619
Steps | Step Details | DTP | QA | Design | IR | DTP Vendor/FL | Design Vendor/FL | Tech Team | PM | Unit of calculation | # units | DTP | QA | Design | IR | DTP Vendor/FL | Design Vendor/FL | Tech Team | PM | DTP | QA | Design | IR | DTP Vendor/FL | Design Vendor/FL | Tech Team | PM | Total Estimated Required Budget
Print
Book (Print Asset) - Identify negative credits & images |  | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Book | 100 | 7.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Book (Print Asset) - Rebranding of book (covers & initial pages) |  | 0.14286 | 0 | 0 | 0 | 0.28571 | 0 | 0 | 0 | Book | 100 | 14.2857 | 0 | 0 | 0 | 28.5714 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 64285.7143 | 0 | 0 | 0 | 114285.7143
QA |  | 0 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | Book | 100 | 0 | 7.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
QA CI |  | 0.095238 | 0 | 0 | 0 | 0.19048 | 0 | 0 | 0 | Book | 100 | 9.5238 | 0 | 0 | 0 | 19.0476 | 0 | 0 | 0 | 33333.3333 | 0 | 0 | 0 | 42857.1429 | 0 | 0 | 0 | 76190.4762
QA CIC and Sign-off |  | 0 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | Book | 100 | 0 | 7.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
Ripping Approvals |  | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Book | 100 | 14.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000
Digital |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MP4s (Digital Asset) - Rebranding of videos (Simpler Ones) |  | 0 | 0 | 0 | 0 | 0 | 0.071429 | 0 | 0 | Asset | 1000 | 0 | 0 | 0 | 0 | 0 | 71.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160714.2857 | 0 | 0 | 160714.2857
MP4s (Digital Asset) - Rebranding of videos (Tricky Ones) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Asset | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530000
PDFs (Digital Asset) - Rebranding of PDFs |  | 0.002381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Asset | 5700 | 13.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47500
HTMLs (Digital Asset) - Rebranding of HTMLs |  | 0 | 0 | 0 | 0.011905 | 0 | 0 | 0 | 0 | Asset | 4423 | 0 | 0 | 0 | 52.6548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144800.5952 | 0 | 0 | 0 | 0 | 144800.5952
Update the Epub | Add new ISBN of rebranded book to existing book Replace old cover with new cover Hide Initial Pages Replace Assets Replace inside pages where negative credit was present (very rare) | 0.02381 | 0.14286 | 0 | 0 | 0 | 0 | 0.059524 | 0 | Book | 65 | 1.5476 | 9.2857 | 0 | 0 | 0 | 0 | 3.869 | 0 | 5416.6667 | 32500 | 0 | 0 | 0 | 0 | 38690.4762 | 0 | 76607.1429
QA of Epub and Sign-off |  | 0 | 0.57143 | 0 | 0 | 0 | 0 | 0.02381 | 0 | Book | 65 | 0 | 37.1429 | 0 | 0 | 0 | 0 | 1.5476 | 0 | 0 | 130000 | 0 | 0 | 0 | 0 | 15476.1905 | 0 | 145476.1905
CTRBs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rebranding CTRBs |  | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CTRB | 76 | 5.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19000
QA and Sign-off |  | 0.035714 | 0.035714 | 0 | 0 | 0 | 0 | 0 | 0 | CTRB | 76 | 2.7143 | 2.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 19000
Project Management |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | Book | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57142.8571 | 57142.8571