## Summary
Summary of Product Changes | Budget Needed |  |  |  |  | Resources Needed from PP Team |  | Timelines | Summary of LEAD Themes
|  |  |  | 8498832 | [5 empty] | Nursery Current Themes | Proposed Theme / Title | Jr KG Current Themes | Proposed Theme / Title | Sr KG Current Themes | Proposed Theme / Title
Print (Student Reader + Workbook) |  | Print | Digital | Total | % | Print |  | Print | Unit 1 | Falling in love with school | Me in My School | Falling In Love With School | Falling In Love With School | Me and my school | My Body is a Wonder
Major Academic continuity retained | Academic (Creator & Reviewer) | 3060000 | 3221400 | 6281400 | 73.91% | Creator | 2 | Term 1 | Unit 2 | My Myself | Special Me | My Family and My Home | My Loving World: Family and Friends | Community | Places and People
15% changes in learning outcomes and progression sequence across 3 levels (Nur, JKG, SKG) | DTP+Design | 1100400 | 566400 | 1666800 | 19.61% | Reviewer 1 | 1 | Term 2 | Unit 3 | My Body and senses | My Body and senses | My Body and Senses | I am Unique! | Sharing the Planet (Animals) | Sharing the Planet (Animals)
Same integrated EVS approach and pedagogy | Edit | 58560 | 0 | 58560 | 0.689% | Reviewer 2 | 1 |  | Unit 4 | My Home and Family | My Little World | Homes | Homes and Habitats | Our Place in the Universe | Our Place in the Universe
Refreshed Book Designs including covers, reducing initial pages, page template change, book size change | QA | 34650 | 37422 | 72072 | 0.848% |  |  | Digital | Unit 5 | Community | Community & Transport | Community | Our Community & Country | Food Sources | Food Sources
Internal Reader and Workbook refreshed with 25% changes (new worksheet or edit worksheets) | Project Management | 210000 | 210000 | 420000 | 4.942% | Digital |  | Term 1 | Unit 6 | Animals | The World of Animals | Water | Water & Land | Water | Land & Water
Revised book sequencing |  | 4463610 | 4035222 | 8498832 |  | Creator | 2 | Term 2 | Unit 7 | Food | Food | Food | Health & Food | Transport and Communication | The World Moves
Rewritten LPs using updated activities / goals (where feasible) | [5 empty] | Reviewer | 1
New stories, adding few rhymes and songs (from the internet, not building it ourselves)
New Assessment Cards and backend recording systems for Assmt (further clarity in Spec Stage) | [9 empty] | No Changes (everything retained) | Name Changes (Only Name refreshed) | Minor Change (2-3 LI-LO added to the same theme for better coverage) | Major Changes (Substantial changes to the theme and has implied changes) | New
Add Milestone cards and detailed index to books - 1 page each | [9 empty] | 3 | 6 | 9 |  | 3
Increased Pages in books for writing (included in point on Row 8)
Theme Changes - No Change, Name Change, Minor Change, Major Change detailed table below (Grid Q1)
Field team training and deployment
Marketing look and feel - New Value Proposition
Assessment Backend - Tech
Budget backwards: 1. Introduction of new CRLs 2. LP simplification (AI Based only)
Digital
Pedagogy retained. Sequencing aligned. Limited rebuild.
Unit and day plan sequencing updated LI-LO, LP, CRL, TR, Assmt where goal changes are seen -
Day plan content modified where required
CRL, PPTVO and assessments restructured to align with new book flow due to goal changes / theme changes
Add ‘Share the WOW moment” nudges in the lesson plans

## Scope and Volume
Grade | Scope | Creation | Print | [10 empty] | Digital
|  |  | No. of Books |  |  | Total No. of Units |  |  |  | No. of Pages |  |  | Print Cycle Requirements | Day Allocations | Video Resources (AVCs + PPTVOs) | Concept CRLS
|  |  | SR | WB | WrB | Term 1 + Term 2 Split | SR | WB | Wr | SR | WB | Wr |  | 1 Unit = 20 Days | 1 per block (5 days) 4 per Unit of 20 days | ~ 20 per Unit
SKG | Print + Digital | Student Reader + Workbook + Writing Book(Wr B) | 2 | 4 | 1 | Term 1 - 4 Units Term 2 - 3 Units | 7 | 7 | 7 | 176 | 392 | 76 | Edit: - Edit of Unit content - Book Hygiene Check DTP : -New PPT Template -Book Covers Design Team: -Shutterstock images -Illustrations | 144
JKG | Print + Digital | Student Reader + Workbook + Writing Book(Wr B) | 2 | 4 | 1 | Term 1 - 4 Units Term 2 - 3 Units | 7 | 7 | 7 | 184 | 368 | 76 |  | 144
Nursery | Print + Digital | Student Reader + Workbook + Writing Book(Wr B) | 2 | 4 | 1 | Term 1 - 4 Units Term 2 - 3 Units | 7 | 7 | 7 | 136 | 296 | 76 |  | 144
|  | Total |  |  |  |  | 21 | 21 | 21 | 496 | 1056 | 228 |  | 432 | 0 | 0

## Budget
Cost per role
Product Changes |  | (Norms per unit in mandays) | [8 empty] | (Total # required mandays) | [6 empty] | 100000 | 120000 | 360000 | 80000 | 80000 | 80000 | 55000 | 8498832
Elements of Product | Digital / Print | Creator | Reviewer 1 | Reviewer 2 | Design | DTP | Edit | QA | Unit of calculation | # units | Creator | Reviewer 1 | Reviewer 2 | Design | DTP | Edit | QA | Creator | Reviewer 1 | Reviewer 2 | Design | DTP | Edit | QA | Total Estimated Required Budget | 1.2
A. Student Reader (SR) | [24 empty] | 1923180
Milestone Pages | Print | 0.5 | 0 | 0.25 | 0.25 | 0 | 0 | 0 | Milestone Pages | 21 | 10.5 | 0 | 5.25 | 5.25 | 0 | 0 | 0 | 63000 | 0 | 113400 | 25200 | 0 | 0 | 0 | 201600
Chapter level changes for Cluster 1 | Print | 2 | 0.5 | 0 | 0 | 1.5 | 0 | 0 | Unit | 9 | 18 | 4.5 | 0 | 0 | 13.5 | 0 | 0 | 108000 | 32400 | 0 | 0 | 64800 | 0 | 0 | 205200
Chapter level changes for Cluster 2 | Print | 2.75 | 0.75 | 0 | 0.5 | 2 | 0.3 | 0 | Unit | 9 | 24.75 | 6.75 | 0 | 4.5 | 18 | 2.7 | 0 | 148500 | 48600 | 0 | 21600 | 86400 | 12960 | 0 | 318060
Chapter level changes for Cluster 3 | Print | 4.75 | 2.25 | 0 | 1 | 1.25 | 0.8 | 0 | Unit | 3 | 14.25 | 6.75 | 0 | 3 | 3.75 | 2.4 | 0 | 85500 | 48600 | 0 | 14400 | 18000 | 11520 | 0 | 178020
Initial Pages (8 pages) | Print | 0 | 0 | 4 | 5 | 0 | 0 | 0 | Book | 1 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 86400 | 24000 | 0 | 0 | 0 | 110400
Chapter Level design | Print | 0 | 3.5 | 0 | 3 | 0 | 0 | 0 | Book | 1 | 0 | 3.5 | 0 | 3 | 0 | 0 | 0 | 0 | 25200 | 0 | 14400 | 0 | 0 | 0 | 39600
Book level changes | Print | 1 | 2 | 3 | 2 | 4 | 0 | 0.5 | Book | 6 | 6 | 12 | 18 | 12 | 24 | 0 | 3 | 36000 | 86400 | 388800 | 57600 | 115200 | 0 | 9900 | 693900
Assessment Card | Print | 1 | 0 | 2 | 1.5 | 0 | 0.5 | 0 | Level | 3 | 3 | 0 | 6 | 4.5 | 0 | 1.5 | 0 | 18000 | 0 | 129600 | 21600 | 0 | 7200 | 0 | 176400
B. Workbook (WB) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 2188680
Chapter level changes for Cluster 1 | Print | 2 | 0.5 | 0 | 0 | 1.5 | 0 | 0 | Unit | 9 | 18 | 4.5 | 0 | 0 | 13.5 | 0 | 0 | 108000 | 32400 | 0 | 0 | 64800 | 0 | 0 | 205200
Chapter level changes for Cluster 2 | Print | 2.75 | 0.75 | 0 | 0.5 | 2 | 0.3 | 0 | Unit | 9 | 24.75 | 6.75 | 0 | 4.5 | 18 | 2.7 | 0 | 148500 | 48600 | 0 | 21600 | 86400 | 12960 | 0 | 318060
Chapter level changes for Cluster 3 | Print | 4.75 | 2.25 | 0 | 1 | 1.25 | 0.8 | 0 | Unit | 3 | 14.25 | 6.75 | 0 | 3 | 3.75 | 2.4 | 0 | 85500 | 48600 | 0 | 14400 | 18000 | 11520 | 0 | 178020
Initial Pages (4 pages) | Print | 0 | 0 | 2 | 3 | 0 | 0.5 | 0 | Book | 1 | 0 | 0 | 2 | 3 | 0 | 0.5 | 0 | 0 | 0 | 43200 | 14400 | 0 | 2400 | 0 | 60000
Chapter Level design | Print | 0 | 3.5 | 0 | 3 | 0 | 0 | 0 | Book | 1 | 0 | 3.5 | 0 | 3 | 0 | 0 | 0 | 0 | 25200 | 0 | 14400 | 0 | 0 | 0 | 39600
Book level changes | Print | 1 | 2 | 3 | 2 | 4 | 0 | 0.5 | Book | 12 | 12 | 24 | 36 | 24 | 48 | 0 | 6 | 72000 | 172800 | 777600 | 115200 | 230400 | 0 | 19800 | 1387800
C. Writing Book | [24 empty] | 141750
Chapter level changes | Print | 2 | 2 | 0 | 1 | 3 | 0 | 0.5 | Book | 3 | 6 | 6 | 0 | 3 | 9 | 0 | 1.5 | 36000 | 43200 | 0 | 14400 | 43200 | 0 | 4950 | 141750
D. Digital |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3825222
Blueprint Mapping | Digital | 0 | 0 | 3 | 0 | 0 | 0 | 0 | Unit | 21 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 1360800 | 0 | 0 | 0 | 0 | 1360800
Bridge Course | Digital | 1 | 0.5 | 0 | 0 | 0 | 0 | 0.03 | Unit | 3 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0.09 | 18000 | 10800 | 0 | 0 | 0 | 0 | 297 | 29097
Day plan Content Changes for Cluster 1 | Digital | 4.3 | 2.5 | 0 | 0 | 0 | 0 | 0.5 | Unit | 9 | 38.7 | 22.5 | 0 | 0 | 0 | 0 | 4.5 | 232200 | 162000 | 0 | 0 | 0 | 0 | 14850 | 409050
Day plan Content Changes for Cluster 2 | Digital | 7.45 | 3.5 | 0 | 0.25 | 0 | 0 | 0.25 | Unit | 9 | 67.05 | 31.5 | 0 | 2.25 | 0 | 0 | 2.25 | 402300 | 226800 | 0 | 10800 | 0 | 0 | 7425 | 647325
Day plan Content Changes for Cluster 3 | Digital | 12.75 | 6.5 | 0 | 0.5 | 0 | 0 | 1.5 | Unit | 3 | 38.25 | 19.5 | 0 | 1.5 | 0 | 0 | 4.5 | 229500 | 140400 | 0 | 7200 | 0 | 0 | 14850 | 391950
Concept CRL & PPTVO (For all 3 clusters) | Digital | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | Unit | 36 | 36 | 0 | 0 | 18 | 0 | 0 | 0 | 216000 | 0 | 0 | 86400 | 0 | 0 | 0 | 302400
Fresh Video resources (AVCs) (For all 3 Clusters) | Digital | 0.8 | 0 | 0 | 6 | 0 | 0 | 0 | AVC | 15 | 12 | 0 | 0 | 90 | 0 | 0 | 0 | 72000 | 0 | 0 | 432000 | 0 | 0 | 0 | 504000
Modified Video resources (AVCs) (For all 3 Clusters) | Digital | 0.5 | 0 | 0 | 0.25 | 0 | 0 | 0 | AVC | 25 | 12.5 | 0 | 0 | 6.25 | 0 | 0 | 0 | 75000 | 0 | 0 | 30000 | 0 | 0 | 0 | 105000
Assessments | Digital | 0.3 | 0.25 | 0 | 0 | 0 | 0 | 0 | Unit | 21 | 6.3 | 5.25 | 0 | 0 | 0 | 0 | 0 | 37800 | 37800 | 0 | 0 | 0 | 0 | 0 | 75600
E. PM | [24 empty] | 420000

## Norms
|  | *Norms per unit in mandays | [6 empty] | 1
Elements of Product | Unit of calculation | Creator | Reviewer 1 | Reviewer 2 | Design | DTP | Edit | QA |  | Original norms
A. Student Reader (SR)
Chapter level changes for Cluster 1 | Unit | 2 | 0.5 | 0 | 0 | 1.5 | 0 | 0 |  | 2 | 0.5 | 0 | 0 | 1.5 | 0 | 0
Chapter level changes for Cluster 2 | Unit | 2.75 | 0.75 | 0 | 0.5 | 2 | 0.3 | 0 |  | 2.75 | 0.75 | 0 | 0.5 | 2 | 0.3 | 0
Chapter level changes for Cluster 3 | Unit | 4.75 | 2.25 | 0 | 1 | 1.25 | 0.8 | 0 |  | 4.75 | 2.25 | 0 | 1 | 1.25 | 0.8 | 0
Milestone Pages | Milestone Pages | 0.5 | 0 | 0.25 | 0.25 | 0 | 0 | 0 |  | 0.5 | 0 | 0.25 | 0.25 | 0 | 0 | 0
Assessment Card | Level | 1 | 0 | 2 | 1.5 | 0 | 0.5 | 0 |  | 1 | 0 | 2 | 1.5 | 0 | 0.5 | 0
Initial Pages (8 pages) | Book | 0 | 0 | 4 | 5 | 0 | 0 | 0 |  | 0 | 0 | 4 | 5 | 0 | 0 | 0
Chapter Level design | Book | 0 | 3.5 | 0 | 3 | 0 | 0 | 0 |  | 0 | 3.5 | 0 | 3 | 0 | 0 | 0
Book level changes | Book | 1 | 2 | 3 | 2 | 4 | 0 | 0.5 |  | 1 | 2 | 3 | 2 | 4 | 0 | 0.5
B. Workbook (WB) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chapter level changes for Cluster 1 | Unit | 2.5 | 0.5 | 0 | 0 | 1.5 | 0 | 0 |  | 2.5 | 0.5 | 0 | 0 | 1.5 | 0 | 0
Chapter level changes for Cluster 2 | Unit | 3.25 | 1 | 0 | 0.5 | 2.5 | 1 | 0 |  | 3.25 | 1 | 0 | 0.5 | 2.5 | 1 | 0
Chapter level changes for Cluster 3 | Unit | 6.5 | 2 | 0 | 1 | 2.5 | 1.5 | 0 |  | 6.5 | 2 | 0 | 1 | 2.5 | 1.5 | 0
Initial Pages (4 pages) | Book | 0 | 0 | 2 | 3 | 0 | 0.5 | 0 |  | 0 | 0 | 2 | 3 | 0 | 0.5 | 0
Chapter Level design | Book | 0 | 1.5 | 0 | 3 | 0 | 0 | 0 |  | 0 | 1.5 | 0 | 3 | 0 | 0 | 0
Book level changes | Book | 1 | 2 | 3 | 2 | 4 | 0 | 0.5 |  | 1 | 2 | 3 | 2 | 4 | 0 | 0.5
C. Writing Book |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chapter level changes | Book | 2 | 2 | 0 | 1 | 3 | 0 | 0.5 |  | 2 | 2 | 0 | 1 | 3 | 0 | 0.5
D. Digital |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blueprint Mapping | Unit | 0 | 0 | 3 | 0 | 0 | 0 | 0 |  | 0 | 0 | 3 | 0 | 0 | 0 | 0
Bridge Course | Unit | 1 | 0.5 | 0 | 0 | 0 | 0 | 0.03 |  | 1 | 0.5 | 0 | 0 | 0 | 0 | 0.03
Day plan Content Changes for Cluster 1 | Unit | 4.3 | 2.5 | 0 | 0 | 0 | 0 | 0.5 |  | 4.3 | 2.5 | 0 | 0 | 0 | 0 | 0.5
Day plan Content Changes for Cluster 2 | Unit | 7.45 | 3.5 | 0 | 0.25 | 0 | 0 | 0.25 |  | 7.45 | 3.5 | 0 | 0.25 | 0 | 0 | 0.25
Day plan Content Changes for Cluster 3 | Unit | 12.75 | 6.5 | 0 | 0.5 | 0 | 0 | 1.5 |  | 12.75 | 6.5 | 0 | 0.5 | 0 | 0 | 1.5
Concept CRL & PPTVO (For all 3 clusters) | Unit | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | Reviewer | 2
Fresh Video resources (AVCs) (For all 3 Clusters) | AVC | 0.8 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0.8 | 0 | 0 | 6 | 0 | 0 | 0 |  | 1
Modified Video resources (AVCs) (For all 3 Clusters) | AVC | 0.5 | 0 | 0 | 0.25 | 0 | 0 | 0 |  | 0.5 | 0 | 0 | 0.25 | 0 | 0 | 0
Assessments | Unit | 0.25 | 0.125 | 0 | 0 | 0 | 0 | 0 |  | 0.25 | 0.125 | 0 | 0 | 0 | 0 | 0

## Pre-Primary Digital Norms
Unit LEVEL PROCESS and norms - 1 Unit = 20 LP
| Cluster Description | Cluster | Process | Norm | Responsibility
Digital | 1-Minor Modification | 1 | Chapter creation (LP+Static Resource creation+Answer key of WB) | 2 | Creator | 1- Minor content change + feature addition |  | 9
|  |  | Chapter review | 1 | Reviewer 1 | Creator | 4.35
|  |  | Chapter CI | 1 | Creator | Reviewer 1 | 2.5
|  |  | Chapter CIC | 1 | Reviewer 1 | Design | 0
|  |  | LP Edit 1 | 0 | Edit | DTP | 0
|  |  | LP Edit 1 CI | 0 | Creator | Edit | 0
|  |  | LP Design/Media work | 0 | Design | QA | 0.5
|  |  | LP Design/Media review | 0 | Creator
|  |  | Uploading and tagging | 1 | Creator
|  |  | Internal delta testing | 0.5 | Reviewer 1 | 2. Major Modification |  | 9
|  |  | Internal delta testing CI | 0.25 | Creator | Creator | 7.755
|  |  | Internal delta testing CIC | 0 | Reviewer 1 | Reviewer 1 | 3.5
|  |  | DRC | 0 | QA | Design | 0.25
|  |  | DRC CI | 0 | Creator | DTP | 0
|  |  | TT | 0.5 | QA | Edit | 0
|  |  | TT CI | 0.1 | Creator | QA | 0.25
| 2. Major Modification | 2 | Chapter creation (LP+Static Resource creation+Answer key of WB) | 4 | Creator
|  |  | Chapter review | 1.5 | Reviewer 1 | 3-New chapter and feature addition |  | 9
|  |  | Chapter CI | 1.5 | Creator | Creator | 12.75
|  |  | Chapter CIC | 1 | Reviewer 1 | Reviewer 1 | 6.5
|  |  | LP Edit 1 | 0 | Edit | Design | 0.5
|  |  | LP Edit 1 CI | 0 | Creator | DTP | 0
|  |  | LP Design (Images for static CRL) | 0.25 | Design | Edit | 0
|  |  | LP Design review | 0.125 | Creator | QA | 1.5
|  |  | Uploading and tagging | 1.5 | Creator
|  |  | Internal delta testing | 1 | Reviewer 1 | Digital Elements
|  |  | Internal delta testing CI | 0.5 | Creator | Creator | 1.75
|  |  | Internal delta testing CIC | 0 | Reviewer 1 | Reviewer 1 | 0
|  |  | DRC | 0 | QA | Design | 6.75
|  |  | DRC CI | 0 | Creator | DTP | 0
|  |  | TT | 0.25 | QA | Edit | 0
|  |  | TT CI | 0.13 | Creator | QA | 0
| 3-New chapter and feature addition | 3 | Chapter creation (LP+Static Resource creation+Answer key of WB) | 7 | Creator
|  |  | Chapter review | 3 | Reviewer 1
|  |  | Chapter CI | 2 | Creator
|  |  | Chapter CIC | 1 | Reviewer 1
|  |  | LP Edit 1 | 0 | Edit
|  |  | LP Edit 1 CI | 0 | Creator
|  |  | LP Design/Media work (Images for static CRL) | 0.5 | Design
|  |  | LP Design/Media review | 0.25 | Creator
|  |  | Uploading and tagging | 2 | Creator
|  |  | Internal delta testing | 2 | Reviewer 1
|  |  | Internal delta testing CI | 1 | Creator
|  |  | Internal delta testing CIC | 0.5 | Reviewer 1
|  |  | DRC | 0.5 | QA
|  |  | DRC CI | 0 | Creator
|  |  | TT | 1 | QA
|  |  | TT CI | 0.5 | Creator
| Digital Elements | PPT VO + AVC | PPT Design | 0.5 | Creator
|  |  | VO Design | 0.5 | Creator
|  |  | Stitching | 0.5 | Design
|  |  | AVC mark up/requirement details | 0.25 | Creator
|  |  | AVC fresh creation | 6 | Design
|  |  | AVC Review | 0.5 | Creator
|  |  | AVC Modification | 0.25 | Design

## Pre-Primary Print Norms
Unit LEVEL PROCESS and Norms
| Cluster Description | Cluster | Process | Norm for Reader | Norm for Workbook | Responsibility
CHAPTER LEVEL Norms are defined at a chapter level | 1-Minor Modification | 1 | New Content Check+New feature Check | 0.5 | 1 | Creator | 1- Minor content change + feature addition |  | 9
|  |  | Ready for R1 | 0 | 0 | Creator |  | Reader | Workbook
|  |  | Chapter R1 (Direct Review and Changes) | 0.5 | 0.5 | Reviewer 1 | Creator | 2 | 2.5
|  |  | Chapter CI | 0 | 0 | Creator | Reviewer 1 | 0.5 | 0.5
|  |  | Chapter CIC | 0 | 0 | Reviewer 1 | Design | 0 | 0
|  |  | Design | 0 | 0 | Design | DTP | 1.5 | 1.5
|  |  | Design Check | 0 | 0 | Creator | Edit | 0 | 0
|  |  | Ready for DTP | 0 | 0 | Creator
|  |  | DTP Done | 1 | 1 | DTP | 2-Major modification to content and feature addition |  | 9
|  |  | Chapter Edit | 0 | 0 | Edit |  | Reader | Workbook
|  |  | Edit validation + CI | 0 | 0 | Creator | Creator | 2.75 | 3.25
|  |  | DTP check | 1 | 1 | Creator | Reviewer 1 | 0.75 | 1
|  |  | DTP CI | 0.5 | 0.5 | DTP | Design | 0.5 | 0.5
|  |  | DTP CIC | 0.5 | 0.5 | Creator | DTP | 2 | 2.5
|  |  | Chapter ready for stitching | 0 | 0 | DTP | Edit | 0.3 | 1
| 2. Major Modification | 2 | New Content Check+New feature Check | 1 | 1 | Creator
|  |  | Ready for R1 | 0 | 0 | Creator | 3-New chapter and feature addition |  | 3
|  |  | Chapter R1 (Direct Review and Changes) | 0.5 | 0.75 | Reviewer 1 |  | Reader | Workbook
|  |  | Chapter CI | 0.25 | 0.25 | Creator | Creator | 4.75 | 6.5
|  |  | Chapter CIC | 0.25 | 0.25 | Reviewer 1 | Reviewer 1 | 2.25 | 2
|  |  | Design | 0.5 | 0.5 | Design | Reviewer 2 | 0 | 0
|  |  | Design Check | 0.5 | 0.5 | Creator | Design | 1 | 1
|  |  | Chapter Edit | 0.3 | 1 | Edit | DTP | 1.25 | 2.5
|  |  | Chapter Edit CI | 0.25 | 0.5 | Creator | Edit | 0.8 | 1.5
|  |  | Chapter Edit CIC | 0 | 0 | Edit
|  |  | Ready for DTP | 0 | 0 | Creator | Initial Pages
|  |  | DTP Done | 1.5 | 2 | DTP |  | Reader | Workbook
|  |  | DTP check | 0.5 | 0.75 | Creator | Creator | 4 | 2
|  |  | DTP CI | 0.5 | 0.5 | DTP | Reviewer 1 | 0 | 0
|  |  | DTP CIC | 0.25 | 0.25 | Creator | Reviewer 2 | 0 | 0
|  |  | Chapter ready for stitching | 0 | 0 | DTP | Design | 5 | 3
| 3-New chapter and feature addition | 3 | New Chapter creation | 1.5 | 2 | Creator | DTP | 0 | 0
|  |  | Ready for R1 | 0 | 0 | Creator | Edit | 0 | 0
|  |  | Chapter R1 (Direct Review, No CI or CIC) | 1.5 | 1.5 | Reviewer 1
|  |  | Chapter CI | 0.75 | 1 | Creator | Milestone Pages
|  |  | Chapter CIC | 0.75 | 0.5 | Reviewer 1 |  | Reader | Workbook
|  |  | Design | 1 | 1 | Design | Creator | 2.25 | 0
|  |  | Design Check | 0.75 | 1 | Creator | Reviewer 1 | 1 | 0
|  |  | Chapter Edit | 0.3 | 1 | Edit | Reviewer 2 | 0.1 | 0
|  |  | Chapter Edit CI | 1 | 1 | Creator | Design | 0.25 | 0
|  |  | Chapter Edit CIC | 0.5 | 0.5 | Edit | DTP | 0 | 0
|  |  | Ready for DTP | 0 | 0 | Creator | Edit | 0 | 0
|  |  | DTP Done | 1 | 1.5 | DTP
|  |  | DTP check | 0.5 | 1 | Creator | Chapter Level
|  |  | DTP CI | 0.25 | 1 | DTP |  | Reader | Workbook
|  |  | DTP CIC | 0.25 | 0.5 | Creator | Creator | 0 | 0
|  |  | Chapter ready for stitching | 0 | 0 | DTP | Reviewer 1 | 3.5 | 1.5
BOOK LEVEL Norms are defined at a book level |  |  | Initial Pages Mark up | 2 | 1 | Reviewer 2 | Reviewer 2 | 0 | 0
|  |  | Initial Pages Creation | 5 | 3 | Design | Design | 3 | 3
|  |  | Initial Pages Review | 2 | 1 | Reviewer 2 | DTP | 0 | 0
|  |  | Chapter Design Mark up | 2 | 1 | Reviewer 1 | Edit | 0 | 0
|  |  | Chapter Design Creation | 3 | 3 | Design
|  |  | Chapter Design Review | 1.5 | 0.5 | Reviewer 1 | Book level
|  |  | Other pages creation (Unit cover+milestone) | 1 | 1 | Creator |  | Reader | Workbook
|  |  | Other pages review | 1 | 1 | Reviewer 1 | Creator | 1 | 1
|  |  | Other pages CI | 0.25 | 0.25 | Creator | Reviewer 1 | 1.7 | 1.7
|  |  | Other pages CIC | 0.1 | 0.1 | Reviewer 2 | Reviewer 2 | 2.5 | 2.5
|  |  | Design Creation for (Unit cover+milestone) | 1 | 0.5 | Design | Design | 2 | 2
|  |  | Design Checks | 0.25 | 0.1 | Creator | DTP | 3.5 | 3.5
|  |  | Book stitching - DTP | 0.5 | 0.5 | DTP | Edit | 0 | 0
|  |  | Book Edit Hygiene Check | 0 | 0 | Edit | QA | 0.5 | 0.5
|  |  | Book Check by Shreya | 2 | 2 | Design
|  |  | Book level Review | 0.5 | 0.5 | Creator
|  |  | Shreya comments + Author comments CI | 0.5 | 0.5 | DTP
|  |  | Shreya comments + Author comments CIC | 0.5 | 0.5 | Creator
|  |  | Book Subject Proofreading R2 | 2 | 2 | Reviewer 2
|  |  | Book Subject Proofreading CI | 0.5 | 0.5 | DTP
|  |  | Book Subject Proofreading CIC | 0.5 | 0.5 | Reviewer 1
|  |  | Book - QA | 0.5 | 0.5 | QA
|  |  | Book - QA comment Validation | 0.5 | 0.5 | Reviewer 1
|  |  | Book - QA CI at DTP | 0.25 | 0.25 | DTP
|  |  | Book - QA CIC | 0.2 | 0.2 | Reviewer 1
|  |  | Book - pre-press | 1 | 1 | DTP
|  |  | Book - pre-press commnts validation | 0.5 | 0.5 | Reviewer 1
|  |  | Book - pre-press CI | 0.75 | 0.75 | DTP
|  |  | Book - pre-press CIC | 0.5 | 0.5 | Reviewer 2
|  |  | Book - Ready for printer | 0 | 0 | DTP

## Quantum(WIP)
Product Changes |  | (Norms per unit in mandays) | [8 empty] | 15th April | 15th Jun | Print: 15 July Digital: 1 Aug | Print: 1 Dec Digital: 1 Jan
Elements of Product | Digital / Print | Creator | Reviewer 1 | Reviewer 2 | Design | DTP | Edit | QA | Unit of calculation | # units | Spec | Solve 1 | Splash 1 | Splash 2
A. Student Reader (SR)
Milestone Pages | Print | 0.5 | 0 | 0.25 | 0.25 | 0 | 0 | 0 | Milestone Pages | 21 | 3 | 0 | 5 | 13 | Delivery | Delivery Type | Quantum | Outertimelines | Start Date | End Date | Total Available Working Days | #Creators' mandays required | #R1s mandays' required | #R2s mandays required | Creator | Reviewer 1 | Reviewer 2
Chapter level changes for Cluster 1 | Print | 2 | 0.5 | 0 | 0 | 1.5 | 0 | 0 | Unit | 9 | 0 | 0 | 3 | 6 | Spec | Print | - Cover, Design, Initial pages - New unit SKG (5 days) - SB + WB - Milestone cards (2-3 units) | 2026-04-15 | 2026-04-01 | 2026-04-08 | 6 | 3.45 | 7.45 | 8.75 | 0.575 | 1.2417 | 1.4583
Chapter level changes for Cluster 2 | Print | 2.75 | 0.75 | 0 | 0.5 | 2 | 0.3 | 0 | Unit | 9 | 0 | 0 | 3 | 6 |  | Digital | New unit of SKG (first 5 days) | 2026-04-15 | 2026-04-09 | 2026-04-10 | 2 | 1.275 | 0.65 | 3 | 0.6375 | 0.325 | 1.5
Chapter level changes for Cluster 3 | Print | 4.75 | 2.25 | 0 | 1 | 1.25 | 0.8 | 0 | Unit | 3 | 0.1 | 0 | 2 | 0.9 | Solve 1 | Print | Milestone cards (SKG (Term 1) + JKG (Term 1)) | 2026-06-15 | 2026-04-15 | 2026-04-17 | 3 | 2 | 0 | 4 | 0.66667 | 0 | 1.3333
Initial Pages (8 pages) | Print | 0 | 0 | 4 | 5 | 0 | 0 | 0 | Book | 1 | 1 | 0 | 0 | 0 |  | Digital | LP of 1 changed unit in 1 grade | 2026-06-15 | 2026-04-18 | 2026-04-25 | 5 | 7.45 | 3.5 | 18 | 1.49 | 0.7 | 3.6
Chapter Level design | Print | 0 | 3.5 | 0 | 3 | 0 | 0 | 0 | Book | 1 | 1 | 0 | 0 | 0 | Splash 1 | Print | SKG - Term 1 JKG - Term 1 | 2026-07-15 | 2026-05-01 | 2026-06-30 | 43 | 58 | 30.5 | 19.25 | 1.3488 | 0.7093 | 0.44767
Book level changes | Print | 1 | 2 | 3 | 2 | 4 | 0 | 0.5 | Book | 6 | 0 | 0 | 2 | 4 |  | Digital | SKG (2 units - 1 constant, 1 changed) JKG (2 units- 1 constant, 1 changed) | 2026-08-01 | 2026-07-01 | 2026-07-25 | 18 | 32.4 | 12.5 | 18 | 1.8 | 0.69444 | 1
Assessment Card | Print | 1 | 0 | 2 | 1.5 | 0 | 0.5 | 0 | Level | 3 | 1 | 2 | 0 | 0 | Splash 2 | Print | All | 2026-12-01 | 2026-08-01 | 2026-10-01 | 44 | 88.05 | 47.05 | 39.25 | 2.0011 | 1.0693 | 0.89205
B. Workbook (WB) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Digital | All | 2026-01-01 | 2026-10-03 | 2026-12-15 | 52 | 173.95 | 64.25 | 24 | 3.3452 | 1.2356 | 0.46154
Chapter level changes for Cluster 1 | Print | 2 | 0.5 | 0 | 0 | 1.5 | 0 | 0 | Unit | 9 | 0 | 0 | 3 | 6
Chapter level changes for Cluster 2 | Print | 2.75 | 0.75 | 0 | 0.5 | 2 | 0.3 | 0 | Unit | 9 | 0 | 0 | 3 | 6
Chapter level changes for Cluster 3 | Print | 4.75 | 2.25 | 0 | 1 | 1.25 | 0.8 | 0 | Unit | 3 | 0.1 | 0 | 2 | 0.9
Initial Pages (4 pages) | Print | 0 | 0 | 2 | 3 | 0 | 0.5 | 0 | Book | 1 | 1 | 0 | 0 | 0
Chapter Level design | Print | 0 | 3.5 | 0 | 3 | 0 | 0 | 0 | Book | 1 | 1 | 0 | 0 | 0
Book level changes | Print | 1 | 2 | 3 | 2 | 4 | 0 | 0.5 | Book | 12 | 0 | 0 | 4 | 8
C. Writing Book
Chapter level changes | Print | 2 | 2 | 0 | 1 | 3 | 0 | 0.5 | Book | 3 | 0 | 0 | 1 | 2
D. Digital |  | 0 | 0 | 0 | 0 |  | 0 | 0
Blueprint Mapping | Digital | 0 | 0 | 3 | 0 | 0 | 0 | 0 | Unit | 21 | 1 | 6 | 6 | 8
Bridge Course | Digital | 1 | 0.5 | 0 | 0 | 0 | 0 | 0.03 | Unit | 3 | 0 | 0 | 1 | 2
Day plan Content Changes for Cluster 1 | Digital | 4.3 | 2.5 | 0 | 0 | 0 | 0 | 0.5 | Unit | 9 | 0 | 0 | 2 | 7
Day plan Content Changes for Cluster 2 | Digital | 7.45 | 3.5 | 0 | 0.25 | 0 | 0 | 0.25 | Unit | 9 | 0 | 1 | 2 | 6
Day plan Content Changes for Cluster 3 | Digital | 12.75 | 6.5 | 0 | 0.5 | 0 | 0 | 1.5 | Unit | 3 | 0.1 | 0 | 0 | 3
Concept CRL & PPTVO (For all 3 clusters) | Digital | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | Unit | 36 | 0 | 0 | 4 | 32
Fresh Video resources (AVCs) (For all 3 Clusters) | Digital | 0.8 | 0 | 0 | 6 | 0 | 0 | 0 | AVC | 15 | 0 | 0 | 3 | 12
Modified Video resources (AVCs) (For all 3 Clusters) | Digital | 0.5 | 0 | 0 | 0.25 | 0 | 0 | 0 | AVC | 25 | 0 | 0 | 3 | 22
Assessments | Digital | 0.3 | 0.25 | 0 | 0 | 0 | 0 | 0 | Unit | 21 |  |  |  | 21
E. PM

## Resource Estimation
Elements of Product | Creator | Reviewer 1 | Reviewer 2 | DTP | Design | Edit | QA
SR | 76.5 | 33.5 | 33.25 | 37.25 | 59.25 | 6.6 | 3
WB | 69 | 45.5 | 38 | 37.5 | 83.25 | 5.6 | 6
Wr | 6 | 6 | 0 | 3 | 9 | 0 | 1.5
Digital | 213.8 | 80.25 | 63 | 118 | 0 | 0 | 11.34
Total Required Mandays | 365.3 | 165.25 | 134.25 | 195.75 | 151.5 | 12.2 | 21.84
No. of months required per resource | 18.265 | 8.2625 | 6.7125
Cost per role/month | 100000 | 120000 | 360000
Total Salary | 1826500 | 991500 | 2416500 | 5234500
Resource Required | 1.5 | 1 | 1

## People Break Up
49,97,000 |  | CTC | Annual
| Creator 1 | 95000 | 950000 | 1140000 | 1140000
| Creator 2 | 95000 | 950000 | 1140000
| Reviewer 1 | 120000 | 1200000 | 1440000 | 1440000
| Reviewer 2 | 300000 | 3000000 | 3600000 | 3600000
|  |  | 6100000 | 7320000 | 6180000
|  |  | 3 persons | 4 persons | 3 persons
515000
5150000